## WBS
. | Feature | Task | Task Description | Estimation(Hrs) | Assingee
User Management | User Registration and login Functionality | App and model migrations | - First create an application: accounts - In accounts application create models: User inheriting AbstractUser, Address. - After creating models, migrate the models . | 1 | Both
|  | Login | for login funcationality, first install django-allauth library. (libraby: https://docs.allauth.org/en/latest/) - after installing library, follow set-up steps of library. (follow step of documentation for integration.) - after set up, override all-auth login template in to project template folder. - test basic functionality of login, then extend view/form for extra validations. - test the funcationality. | 4 | Yash
|  | Logout | -for logout functionality, first need to follow steps to add all-auth logout functionality in settings.py file - after changes in settings.py file need to override all-auth logout template into template file - test the functionality | 1 | Yash
|  | Sign-up | for signup functionality, after installation and library setup. - override all-auth singup template in to project template folder. - test basic functionality of signup, then extend view/form form extra validations. - test the functionality | 5 | Rinki
|  | Forgot Password | for forgot password functionality, - override all-auth reset password template in to project template folder. - test basic functionality of reset password, then extend view/form for extra validations. - test the functionality | 3 | Yash
|  | Change Password | - override all-auth change password template in to project template folder. - for change password functionality , need to override change password form , for validations - test the functionality | 3 | Rinki
| Manage Profile | View Profile | we will use generic view for view profile - create view in views.py, view name: ViewProfile - template name: view_profile.html - URL: '/viewprofile' , set name: viewprofile - To view profile, first need to create view ViewProfile and render a template name view_profile.html in which we want to view the profile - this views data we need to pass into template by a object context parameter - using Jinja template we need to add views data into templates - we need to make URL for view data and use as_view() after that set a name: viewprofile which we can use in templates | 5 | Rinki
|  | Update Profile | For update profile functionality, - Create a class UpdateProfile using generic view UpdateView - Add User model, the fields to update current user details and success url to viewprofile - Setup url path in urls.py as '/update-profile' and fetch id in url path. - Create template update_profile.html and render django form as paragraph - Test the basic funtionality. | 5 | Yash
Product Module | Product Functionality | App and migrations | - First create application: products. - In products application create models: Product, Category, Brand. - After creating models, migrate the models. | 2 | Both
|  | View product Category | For view product category, - create a class Category using generic view Listview - Add Category model, the Name field to be display. - Setup url path in urls.py as '/category' and fetch id in url path. - Create template category.html. - Create a loop for categories and add category url to it which redirect to view_product page of that category - Test the basic funtionality. | 6 | Yash
|  | View Products | For view products functionality, - Create a class ViewProducts using generic view ListView. - Add Product model, the fields success url to view_products - Use get queryset method in view to filter through foreign key of category and brand to display products. - Setup url path in urls.py as '/view-products' and fetch id in url path. - Create template view_products.html and render django form as paragraph - Test the basic funtionality. | 6 | Rinki
|  | Products Detail page | For product detail functionality, - Create a class ViewProductsDetails using generic view DetailView. - Add Product model, the fields and success url to product detail page. - Use get queryset method in view to filter through foreign key of category and brand to display product details. - Setup url path in urls.py as '/view-products' and fetch id in url path. - Create template view_products_detail.html and render django form as paragraph - Test the basic funtionality. | 6 | Yash
|  | Search Products | For search products functionality, product search will be on category, products - Create a method Search. - use icontains method - Test the basic funtionality. | 4 | Rinki
| Manage Product (admin) | Add Product | create a form in form.py class name - Product fields - [name , description , quntity , price , image,category] view.py file - Add products : add_admin_product (create) - we will use custom function base view - redirect url : redirect page to product view page urls.py file - Add product : 'addproduct'/ , name: 'add-product' templates - Add product : product/add_product.html - use form Product into html file - add validation using jquery | 4 | Yash
|  | Update Product | views.py file - Update product: update_admin_product (update) - use fucntional class based view - redirect to the products view page urls.py file - Update product: 'updateproduct/<int:pk>' , name" 'update-product' templates - update product & single product view : product/update_product.html - use form product into html file - add validation using jquery | 4 | Yash
|  | View Product | views.py file - Read products: view_admin_product (list view) - use function class base view urls.py file - Read product: 'viewproduct/' , name: 'view-product' templates - Read product: product/view_product.html - display fields - [ product image , product name , category , price , brand ,is_active , action ( update/delete) | 2 | Yash
|  | Delete product | views.py file - soft delete : soft_delete_product (softdetele) - is_deleted = true show adn product goes to trash page - delete product: delete_admin_product (delete) urls.py file - Soft delete: 'softdelete/<int:pk>' , name: 'soft-delete-product' - Delete product: 'deleteproduct/<int:pk>' name:'delete-product' templates - soft-delete: only delete button - delete product : product/delete_product.html - here we contain one confirmation page | 4 | Yash
|  | Update Category | For update category functionality, Create a function based view update_category. - Use Category form to show brand data. - Upd aterecord in category model. - Redirect to view_categories.html In urls - Settup url as - 'updatecategory/' and name=update-category In HTML - Create category/updatecategory.html in products folder in templates. - Test the basic funtionality. | 4 | Yash
|  | Add Category | For add category functionality, Create a function based view add_category. - Use Category form to show brand data. - Create a new record in category model. - Redirect to view_categories.html In urls - Settup url as - 'add-category/' and name=add-category In HTML - Create category/add-category.html in products folder in templates. - Test the basic funtionality. | 4 | Rinki
|  | View Category | For view brand functionality, Create a function based view view_category. - Featch all the records from brand data - Redirect to view_category.html In urls - Settup url as - 'view-category/' and name=view-brand In HTML - Create category/view_category.html in products template. - List category in a table format - Test the basic funtionality. | 3 | Yash
|  | Delete Category | For view brand functionality, Create a function based view delete_category. - Redirect to view_category.html In urls - Settup url as - 'deletecategory/' and name=delete-category In HTML - Create category/confirm_delete.html in product template. - Test the basic funtionality. | 4 | Yash
|  | View Brand | For update brand functionality, Create a function based view update_brand. - Use Brand form to show brand data - Update the record in brand model. - Redirect to view_brands.html In urls - Settup url as - 'update-brand/' and name=update-brand In form.py - Create a class Brand. - Add field - image, name and products. - All fields are required. - Add validation, placeholder and css class. - Create a Meta class inside Brand, define model and fields mentioned above In HTML - Create brands/update_brand.html in products template. - Render form as paragraph - Test the basic funtionality. |  | Rinki
|  | Update Brand | For update brand functionality, Create a function based view update_brand. - Use Brand form to show brand data - Update the record in brand model. - Redirect to view_brands.html In urls - Settup url as - 'update-brand/' and name=update-brand In form.py - Create a class Brand. - Add field - image, name and products. - All fields are required. - Add validation, placeholder and css class. - Create a Meta class inside Brand, define model and fields mentioned above In HTML - Create brands/update_brand.html in products template. - Render form as paragraph - Test the basic funtionality. |  | Rinki
|  | Add Brand | For add brand functionality, Create a function based view add_brand. - use Brand form to take user input. - Create a new record in brand model. - Redirect to view_brands.html In urls - Settup url as - 'add-brand/' and name=add-brand In HTML - Create brand/add_brand.html in products template. - Render form as paragraph - Test the basic funtionality. | 6 | Rinki
|  | Admin Dashboard | For dashboard functionality, Check if current user is superuser. If Not redirect to index.html - Fetch total count of Banners, Categories, Brands, Products from their table respectively. - redirect to dashboard.html In urls - Settup url as - 'dashboard/' and name=dashboard In HTML - Create dashboard.html in products template. - Create a side navigation bar for Banner, Categories, Brands, Products. - Show total counts of banners, categories, brands and products on the dashboard - Test the basic funtionality. | 5 | Rinki

## Blog Post WBS
Blog Post WBS
Feature | Task | Task Description | Estimation (hr) | Assign
Common Functionality | App and model migrations | - First create application: blog. - In products application create models: User, Blog, Comment, Like. - After creating models, migrate the models.
User Management | Login
Logout
register
Blogs | Blog Create
Blog Update
Blog Read
Blog Delete
Like | User like
Commnent | User Comment

## Sheet4
Date/Time | 2024-01-30 15:15 | Demo of Dash Clothes - E commerce's
| User Management | User Management functionality Changes |  | Fixed
|  | Frontend | Remove unnecessary validation statements before submitting form on signup and update password | FALSE
|  |  | Remove "anonymous user" when user is not logged in | TRUE
|  |  | Add logo on the website with home page redirection | TRUE
|  |  | Remove logout option if user is not logged in and login option if user is logged out | TRUE
|  |  | Open home page of website directly on 127.0.0.1/ i.e. default URL | TRUE
|  |  | Add profile option in header dropdown and remove it from header bar | TRUE
|  |  | Remove register option if user is logged in | TRUE
|  |  | Remove "[example.com]" from email template and customize it according to the website | TRUE
|  | Backend | Add validation in signup page | FALSE
|  |  | Change primary key into username in profile URL | TRUE
|  |  | One user cannot see other user's details | TRUE
|  |  | Add page not found exception - custom page not found | TRUE
|  | UI | Remove breadcrumbs | TRUE
|  |  | Remove unnecessary text and "we accept" payment method" bottom bar | TRUE
|  |  | Show "Coming soon" on home page | TRUE
|  |  | Remove top black bar | TRUE
|  |  | Make signup page UI same as login page | FALSE
|  |  | Make forgot password page UI same as login in page | TRUE

## Tasks
Sr. No. | Module | Feature | Task | Assign
1 | User Authentication | User Registration and login Functionality | Sign-up
Login/Logout
Forgot Password
Change Password
|  | Manage Profile | View profile
Update detalis on profile
2 | Product Module | Product Functionality | View all products
Product have multiple sub categories
Products Detail page
Search Products
|  | Manage Product | View, Edit, Add, Remove Products, Brand, Category - pop up
View, Add, Remove Products to Cart
3 | Order Module | Order Functionality | View Current Order details
View Order History
4 | Section | Banner Configuration | Banner List View
Update Banner Images
|  | Section Configuration | Section List View
Add, Activate, Deactivate Sections
|  | Data | Import/Export Data
5 | Others | Contact us | Contact Us page View
Add User Contact Details

## Project Features
E - Commerce Project Lead : Khusbhu Chauhan , Palak Parmar Developed by : Yash Shah , Rinki Shivani
Module | Feature
User Module | User Registration
User Sign in
User can change password
User can add additional profile details
User can view all the products or categories of product(Landing page)
User have to sign in to purchase product
User can add or remove product into cart
User can see order details of current order
User can see order history
User can see particular product details
User logout
Admin
Admin can view, add or remove products
Configurablee landing page
Add, view, active, deactivate categories of the section
Banner Configuration (List, Add and Update)
Section Configuration (List, Add and Update)
Admin can add -brand ,product or category in section
import or export product data
Visitor
Visitor can view products without login ((Landing Page))
Visitor can search products (Landing Page)
General
product have multiple sub categories
landing page
contact us page